## Slide 1: Website Development Project Management Portfolio
Project: LifeRoots Wellness Design
Project Manager: Femi Kwesi
Email: femi.Kwesi@gmail.com

## Slide 2: LifeRoots Wellness Website Design
Title: LifeRoots Wellness Website Design (www.liferootswellness.com)
Subtitle: Project Management Plan
Tagline: “Quality Delivery of a seamless user experience on time and within budget"

## Slide 3: Introduction & Agenda 01

## Slide 4: Introduction & Agenda
This presentation covers the end-to-end strategy for the LifeRoots Wellness website design from vision to launch.
Agenda
Project Overview
Goals & KPIs
Scope Definition
Agile Methodology
Timeline & Milestones
Team Structure
Communication Plan
Risk Management
Budget
Next Steps

## Slide 5: Project Overview 02

## Slide 6: Project Goals
“Design LifeRoots Wellness website to increase increase conversion rate and create a modern brand identity”
Key Features:
Responsive Design for both mobile and desktop views
Online ordering system
Live agent Chat bot
Membership Portal
Blog
Shopping Cart
Payment Gateway

## Slide 7: SMART Goals & KPI 03

## Slide 8: Initial Scope Definition
SMART Goal | KPI | Target
Increase website & mobile ordering to 30% & 50% respectively in first 6 months | Conversion rate | 5.6% => 7.0%
Reduce bounce rate below 45% | Bounce Rate = (Total # of Single page visits/Total # OF SESSIONS)*100 | < OR = 45%
Achieve 90+ Page Speed Score | GTMetrix Score | Grade of “A” (> OR = 90)
Grow Traffic by 30% in Year 1 | Organic sessions Goggle analytics 4 | +30% YoY

## Slide 9: Project Scope 04

## Slide 10: SCOPE
In-Scope Deliverable
Responsive website for mobile and desktop devices.
Ordering and payment gateway integration.
Blog +Resource Center (5 articles).
SEO Optimization.
Shopping Cart.
Staff Training.
Out-of-Scope Deliverable
Mobile app development.
Social media marketing.
Ongoing content creation
CRM Integration.

## Slide 11: Methodology 05

## Slide 12: The Methodology used on this project is Agile
Why Agile ?
Flexibility for client feedback
Faster issue resolution
Adaptive
Testing, debugging and Development in Phases
Please see Appendix I for scrum workflow

## Slide 13: Sprint Structure Visual
Appendix I

## Slide 14: Project Timeline 06

## Slide 15: Timeline Breakdown
Please see Appendix II for Gantt Chart
Phase | Start Date | End Date | Duration | Deliverable
Discovery | Sep 01, 2024 | Sep 14, 2025 | 14 days | Stakeholders interview, Sitemap, Tech stack selection
Design | Sep 15, 2024 | Oct 05, 2025 | 21 days | Wireframes, UI Kit,
Development | Oct 06, 2025 | Nov 10, 2025 | 35 days | Ordering System, Responsive build, shopping cart
Testing | Nov 11, 2025 | Nov 24, 2025 | 14 days | Performance optimization, Test Reporting, Bug Fixes,
Lunch | Nov 25, 2025 | Dec 01, 2025 | 7 days | Livee website, Analytics, Training

## Slide 16: Timeline Breakdown Visual
Appendix II

## Slide 17: Project Team & Roles 07

## Slide 18: Team Structure
Human Resources: 6 team members @ $20/hrs./week each
Appendix III

## Slide 19: Communication Plan 08

## Slide 20: Communication Plan
Communication Matrix
Purpose | Tools | Frequency
Daily update | Slack | Daily
Task Tracking | Jira | Real-time
Client Reporting | Email & Power BI Dashboard | Bi-Weekly
Sprint Reviews | Zoom | Every 2 Weeks
Risk Alert | Microsoft Teams | As needed

## Slide 21: Risk Management 09

## Slide 22: Risk Management
Risk Matrix
Risk | Probability | Impact | Mitigation Strategy
Scope Creep | High | High | Change request process
Delayed Content Delivery | Medium | Medium | Buffer time & Pre-approved templates
Tech Debt Accumulation | Low | High | Code reviews every sprint
Vendor Delays (Payment Gateway) | Medium | High | Backup Provider (Square/PayPal)

## Slide 23: Risk Response Table
Risk Matrix With Owner
Risk | Owner | Mitigation | Status
Scope Creep | PM | Change Control Process | On track
Vendors Delay | Lead Tech | Backup Provider | Monitoring

## Slide 24: Risk Response Flowchart
Risk Response Process
Appendix IIII

## Slide 25: Budget 10

## Slide 26: Budget Matrix
Cost Breakdown
Category | Budget Allocation | Actual Spending | Variance | Variance % | Key Cost Drivers
Design | $7,200 (15%) | $7,800 | -$600 | -8.3% | UI/UX, Brand identity, Wireframes
Development | $21,600 (45%) | $20,100 | +$1,500 | +7.0% | CMS setup, API integrations
Content | $9,600 (20%) | $10,500 | -$900 | -9.4% | Blog posts, Resource library, SEO
Testing | $4,800 (10%) | $4,200 | +$600 | +12.5% | Automated tests, UAT sessions
Contingency | $4,800 (10%) | $2,600 | +$2,200 | +45.8% | Scope changes, Priority hotfixes
TOTAL | $48,000 | $45,200 | +$2,800 | +5.8% | 

## Slide 27: Budget Breakdown
Budget Breakdown Appendix V

## Slide 28: Budget Alert
Budget Trigger Decision Rule Appendix VI

## Slide 29: Next Steps 11

## Slide 30: Call To Action
Immediate Actions to Launch Success
Action Items | Owner | Deadline | Purpose
1. Sign Project Charter | Sponsor (CEO) | Aug 30, 2024 | Formalize scope, budget, and authority
2. Kick-off Meeting | Project Manager | Sep 1, 2024 | Align team on goals, roles, and processes
3. Sprint 0: Backlog Refinement | Lead Tech | Sep 1-5, 2024 | Finalize user stories, acceptance criteria
4. Design Workshop | UX Lead + Client | Sep 6, 2024 | Approve wireframes and brand guidelines
5. Dev Environment Setup | DevOps Engineer | Sep 3, 2024 | Configure GitHub, staging servers, CI/CD pipeline
6. Content Calendar Freeze | Marketing Manager | Sep 4, 2024 | Lock initial 20 blog topics and resources

## Slide 31: Conclusions
The agile approach employed in this project facilitates adaptability and responsiveness to change, ensuring that the website development aligns closely with stakeholder expectations. Continuous engagement and prioritization of feedback improve overall project success, leading to a high-quality end product that meets the needs of Life Roots Wellness.

## Slide 32: Thank you!
Do you have any questions?
Email: femi.kwesi@gmail.com
+00 000 000 000